## Project plan summary
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Project Settings
Project Owner | Daniel Melgarejo
Start Date | mar 05, 2017 03:10:05 PM
Completion Date | mar 07, 2017 02:35:57 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 48.4 | 26.8 | 41.5
Planned Time | 0.16667 |  | 0.33333
Actual Tiempo |  | 0.25764 | 0.52569
CPI (Cost-Performance Index) |  |  | 0.63
% Reuse | 17.1% | 15.2% | 7.11%
% New Reusable | 63.7% | 0% | 66.4%
Test Defects/KLOC or equivalent | 3.82 | 6.02 | 3.82
Total Defects/KLOC or equivalent | 11.5 | 12 | 11.5
Yield % | 66.7% | 50% | 66.7%
Code Review Rate | 1593 | 433 | 1367
Program Size
| Plan | Actual | A la Fecha
Base (B) | 59 | 59 | 59
Deleted (D) | 0 | 0 | 0
Modified (M) | 10 | 8 | 8
Added (A) | 184 | 158 | 516
Reused (R) | 50 | 39 | 44
Added and Modified (A+M) | 194 | 166 | 524
Total Size (T) | 293 | 256 | 619
Total New Reusable | 123 | 0 | 348
Estimated Proxy Size (E) | 223 | 264 | 612
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.024306 | 0.0375 | 0.076389 | 14.5%
DiseÃ±o | 0.014583 | 0.0125 | 0.046528 | 8.85%
RevisiÃ³n de DiseÃ±o | 0.0048611 | 0.015278 | 0.015278 | 2.91%
CodificaciÃ³n | 0.058333 | 0.042361 | 0.18333 | 34.9%
RevisiÃ³n de CodificaciÃ³n | 0.0048611 | 0.015972 | 0.015972 | 3.04%
CompilaciÃ³n | 0.0013889 | 0 | 0.0034722 | 0.66%
Pruebas | 0.043056 | 0.12569 | 0.13681 | 26%
Postmortem | 0.015278 | 0.0083333 | 0.047917 | 9.11%
Total | 0.16667 | 0.25764 | 0.52569
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 1.11 | 2 | 3 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 1.11 | 0 | 3 | 50%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 2.22 | 2 | 6
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.37 | 1 | 1 | 16.7%
CodificaciÃ³n | 1.11 | 0 | 3 | 50%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.74 | 1 | 2 | 33.3%
Total | 2.22 | 2 | 6
After Development | 0.74 | 0 | 2
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 3.18 | 2.73 | 2.73
Defects/Hour - Code Review | 0 | 0 | 0
Defects/Hour - Compile | 0 | #DIV/0! | 0
Defects/Hour - Test | 0.71 | 0.33 | 0.61
DRL (DLDR/UT) | 4.48 | 8.23 | 4.48
DRL (Code Review/UT) | 0 | 0 | 0
DRL (Compile/UT) | 0 | #DIV/0! | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 02:37 PM el 7/03/2017